## Slide 1: LABOUR INT Labour Market Integration of Migrants. A Multi Stakeholder Approach
2 February 2017 | ETUC | Presenter: Marco Cilento

## Slide 2
10am - Project objectives, activities and partners’ presentation (ETUC)
11am Preparation of the Network Building Conference in Turin (ITC-ILO)
12am Preparation of the Wok Package Expert Group Labour-Int Migration And Skills (FIERI)
2pm Short introduction to the national pilot actions (AGENTURQ, DGB Buildungswerk, FISASCAT/ANOLF, CEPAG, others..,)
4PM CO-BENEFICIARIES COORDINATION

## Slide 3: Project Goals
The objective of the project is to promote programmes for inclusion in the labour market for (the direct benefit of) asylum-seekers and refugees.
It follows up the Joint Statement of European social and economic actors on refugees.
Adapting skills assessment and skills matching instruments to asylum-seekers and refugees and increase capacity of project partners to perform them. (Starting phase)
Building value for asylum-seekers and refugees. (3) pilot actions will be performed. (Main phase)
Building European added-value for businesses, trade unions and their partners. (Follow-up phase)

## Slide 4: Target group
Refugees
People entitled with international protection with right to work
Asylum-seekers who acquired a right to work
What about preapring for work those who don’t have a right to work yet?

## Slide 5: Description
Building on the interest and capacities of businesses, chambers of industry and commerce, trade unions and migrant associations, the project promotes multi-layered integration paths, from arrival up to the workplace, passing through education, training and job placement. The action includes 3 national pilot actions.
MAIN DELIVERABLES
1 Network Building Package including a permanent steering committee, 1 conference, a dedicated website and enhancement of communication tools of project partners
1 Expert group on Migration and Skills whose results will be made available for pilot actions
3 national multi-stakeholder pilot actions in Germany, Belgium and Italy ... others?
A dissemination package will include dissemination seminar, report on challenges, policy drivers, working tools to perform skills assessment and skills matching of asylum-seekers and refugees,
  1 report on EU best practices of multi-stakeholder approach to labour market integration of migrants,
  1 working plan to disseminate results and spread best practices.

## Slide 6: Methodology
Network building: identification of challenges, policy drivers and common working plans. All the actions are multi-stakeholder.
Capacity building: pinpoints on on-going actions and upgrades capacities already in place. Work packages are based on the concept of improving-by-doing.
Result-oriented pilot actions: Selection criteria: more favourable environment, existence of structured labour market policies, larger presence of asylum-seekers and consolidated presence of partners’ networks. They adapt existing methodologies (e.g. for disadvantaged unemployed) to the specific conditions of asylum-seekers and refugees.
Working tools for skills assessment and skills matching. Experts shall provide new instruments to perform assessment of skills in their activities, aiming at facilitating skill matching for asylum-seekers and refugees. Capitalising on the work done by ETF, CEDEFOP and the EQF.

## Slide 7: Competitive Analysis
Other actors:
At European level: European Commission, Cedefop, ETF. At National level: PES, NGOs, national social partners.
However the project should be meant as an open platform of homogenous interests. Our ambition is to offer the largest number of opportunities to asylum seekers and refugees.
Strengths:
Project partners have sound capacities to disseminate and mobilise their constituencies in all EU Countries. Businesses and trade unions co-regulate the labour market and already work with the migrant population through their dedicated structures (contact points, targeted programmes, services, etc.).
We can be result-oriented while preserving a multi-stakeholder approach
Weaknesses:
Poor impact of current instruments for labour inclusion. Theoretical complexity but little numbers.
Not easy to find refugees to be involved. The reality is more complex than the one depicted in our project.
Are we really able to find workplaces ready to welcome refugees?

## Slide 8: Steering Committee
RESTRICTED
- composed by ETUC, CEEP, EUROCHAMBRES, together with OSCE, UEAPME, ILO-BRUSSELS, UEAPME and BusinessEurope.
FULL
Composed by all co-applicants and “invited” associated organisations
Co-applicants: ETUC, CEEP, EUROCHAMBRES, ITC-ILO, DIESIS, FIERI, DGB Buildungswerk, AgenturQ, FISASCAT/ANOLF, CEPAG, CITUB.
Associated Organisations: OSCE, BusinessEurope, UEAPME, ILO, + 35 supporting organisations.

## Slide 9: WORK PACKAGE 1 (Operated by ITC-ILO)
A network building conference will be organised in Turin at the ITC-ILO centre
2,5 days
5 working languages
80 people
ITC-ILO will prepare materials to introduce plenary sessions and working groups and working sheets to help a result-oriented debate. Methodology and results will be included in the final report of the conference.
Output: Labour-INT Network Building Report.
Resources
Notes: 30 employer representatives, 20 trade union representatives, 10 UnionMigrantNet contact points, 10 local authorities/labour market institutions, 10 European/international organisations

## Slide 10: WORK PACKAGE 2 (Operated by FIERI)
The objective is to set tools to profile skills of asylum-seekers and refugees along the entire integration chain which may include language learning, civic education, social assistance, VET, balance of competences, labour market active participation, having as a output a CV that is recognised by the local labour market and used for skill matching.
Capitalising on existing policy frameworks
Group of specialists from ETUC, EUROCHAMBRES, CEEP, ITC-ILO. ETF, CEDEFOP and EC Services (if relevant). National experts will be appointed by project partners.
Leading organisation: FIERI.
FIERI can involve in-house academic expertise within its international network to deepen analysis on adaptability of the methodology developed in different national contexts.
Notes: 30 employer representatives, 20 trade union representatives, 10 UnionMigrantNet contact points, 10 local authorities/labour market institutions, 10 European/international organisations

## Slide 11: Start up - Network Building – Capacity building (Dec 2016 – Sept 2017)
February ‘17
Kick off meeting steering committee
March ‘17
Last week: Network Building Conference
April’17
First Meeting working group migration and skills
June ‘17
Second Meeting working group migration and skills
September ‘17
Delivering of the report of Group of experts

## Slide 12: Pilot actions – capacity building from (Oct 2017 - May 2018)
October ‘17
Steering Committee
November ‘17
Deployment pilot actions
April ‘18
Second national meeting
May ‘18
Issuing national reports
First meeting of national actions

## Slide 13: Dissemination (Dec 2016 – Sept 2017)
June ‘18
Eurochambres in Vienna
October ‘18
November ‘18
UnionMigrantNet in Sophia
OSCE in Vienna
End of the project
September
CEEP in Stockholm

## Slide 14: Work Package 1 Resources (76,600Euro)
70 trips reimbursed max 300Euro (Trips are managed by the ETUC)
Accommodation 140 nights and 72Euro per person per day
Plenary room + 3 smaller rooms
Interpretation, 5 languages (EN, FR, IT, DE, SP, SW), 10 interpreters, per 3 days
Translations 4 pages

## Slide 15: Work Package 2 Resources (67,000Euro)
10*2 trips reimbursed max 350Euro
15*2 DSA max 30 Euro
10*2 Hotel max 130Euro
Meeting rooms
Working language English
Translations 260 pages
2 In-House Consultants
Composition: FIERI, Agnes Roman and Marco Cilento (ETUC), Ariel Castro (ITC-ILO), Yuliya Simeonova (CITUB – BG), Juliette Loppe’ (Eurochambres) + CEDEFOP + ETF + 2 experts. National partners can be invited as well according to budget contraints.

## Slide 16
Network building conference
Skills and migration group
Language support
Steering committee
Best Practice
Italy
Multis takeholder meeting
Final Report
IT TOOL
Meet Refugees
To local level
Enterprises and Skill needs
Insert profiles
Website
Web tool
Project facilities
Guidelines
Communication
Multi stakeholder approach
Best Practice
Germany
Multis takeholder meeting
Best Practice
Belgium
Multis takeholder meeting
OTHERS
DISSEMINATION
Common tool for skill profiling and skill matching
TIMELINE
2017
2018
VIENNA
OSCE
SOPHIA
CITUB
STOCKHOLM
CEEP
Vienna EUCHAMB